Carol Volker

M.A. Project Proposal

July 28, 2006

Every morning after I wake up, I look out the bedroom window and try to take in everything. I have to remind myself that what I see is real. I live in the country now.

For the last few years, my husband and I have been dreaming about having our own little farm, so we packed up our cats and rabbits and moved to Copper Hill – a tiny town in southwestern Virginia with a post office, a gas station, and lots and lots of cows. But the land is only land. We want to build a farm – Loafkeeper Farm we call it – that will provide us with food and a little income, too.

This is farm country we live in, so it’s not surprising that many other people here have the same ideas we do. Most houses have a garden, and roadside stands are common sights. Nearby cities support several farmers’ markets, and smaller grocery stores carry local produce. Michigan winter daydreams of selling our produce at a little shop at the end of our driveway are suddenly being placed up against reality, and it’s not pretty.

Problem Definition

For Loafkeeper Farm to succeed as a small-scale business, we must Lack of well-defined plans and goals prevent Loafkeeper Farm from taking off.

Solution

Develop a sound business plan to guide Loafkeeper Farm to success.

- What to sell

- Where and how to sell it

- How much do we need to break even; make a profit

- And much, much more

This plan will be for personal use and not to obtain financial assistance.

Project Deliverables

The final project package will contain a business plan for Loafkeeper Farm, _______ and ________ papers from my graduate coursework at Eastern Michigan University, and a self analysis essay. (?)

Currently, I expect the business plan to contain the following parts; however, the items included may change following further research.

- Business / executive summary

- Mission statement and goals

- Financial plan

- Marketing plan

- Personnel plan

- Market production plans for the first 3-5 years

The time line and basic outline of tasks follows. The deadlines for submission of the final proposal and project are noted as “To Be Determined” since these deadlines are dependent on the schedule of the advisor. As previously noted, the Project Development section may change as I complete the work outlined in the Research section.

My goal is to complete the entire project before I apply for admission to the agriculture program at Virginia Tech; the date for application is March 1, 2007.

| Due Date | Status | Task |
| --- | --- | --- |
| Proposal Prep |
| 14 July 06 | Done | Contact advisor with go ahead |
| 14 July 06 | Done | Prepare rough outline for proposal and send to advisor |
| 24 July 06 | In progress | Locate references for writing business plan |
| 24 July 06 | In progress | Read, read, read and write up notes – Business Plan |
| 28 July 06 | In progress | Submit first draft of proposal to advisor |
| TBD |  | Revise proposal and submit to advisor (repeat until done) |
| Research |
| 24 July 06 | In progress | Collect documentation on area farmers’ markets: rules, applications... |
| 24 July 06 | In progress | Read, read, read and write up notes – Markets, etc. |
| 29 Sep 06 |  | Research users / customers and write up conclusions |
| 29 Sep 06 |  | Research competition and write up conclusions |
| 29 Sep 06 | In progress | Observe area farmers’ markets and write up observations |
| 27 Oct 06 |  | Analyze resources and needs for various options |
| 27 Oct 06 |  | Complete analysis of which products to sell and where/how |
| Project Development (tentative) |
| 10 Nov 06 |  | Draft Business summary |
| 10 Nov 06 |  | Draft Mission / Goals |
| 10 Nov 06 |  | Draft Financial Plan |
| 10 Nov 06 |  | Draft Marketing Plan |
| 10 Nov 06 |  | Draft Market Production Plans for next 3-5 years |
| 10 Nov 06 |  | Draft Personnel / Personal Plan |
| 17 Nov 06 |  | Submit first draft of business plan to advisor |
| 1 Dec 06 |  | Prepare old class projects |
| TBD |  | Revise and resubmit plan to advisor until approved |
| TBD |  | Self Analysis |
| 1 Feb 07 |  | Submit completed package to advisor in time for application for Fall 07 semester at VT (March 1, 2007) |

Additional Commitments

Based on my previous attempts to finish this project, I decided to set down some terms to help keep me on track. This may seem a bit weird, but I think it will work for me.

- I will communicate with my advisor no less than once every seven days.

- I will notify my advisor if I will be unable to meet my projected deadlines or if any dates or tasks on my proposed timeline need modifying.

- I will spend a minimum of 30 minutes per day working on the project, and in addition I will record my progress in my education blog every day (education.loafkeeper.com).

- I will finish this project in time to write “M.A. degree to be conferred on ???, 2007” on my application for the Fall 07 semester at Virginia Tech, which is due March 1, 2007.

Bibliography

The farm market cookbook : conversations, recipes, cooking tips, growing hints, mail order sources, a geographical guide, and everything else you should know about American farmers' markets / Judith Olney ; photos by Judith Olney. Publication info. New York, N.Y. : Doubleday, c1991

Farmers' markets : an American success story / Harriet Festing. Publication info. Bath, England : Eco-logic Books, 1998.

Marketing your business : a guide to developing a strategic marketing plan / Ronald A. Nykiel. Publication info. New York : Best Business Books, c2003.

Egg marketing : a guide for the production and sale of eggs. Publication info. Rome : Food and Agriculture Organization of the United Nations, 2003.

Small-scale poultry production : technical guide / E.B. Sonaiya, S.E.J. Swan. Publication info. Rome : Food and Agriculture Organization of the United Nations, 2004.

Business development : a guide to small business strategy / David Butler. Publication info. Oxford : Butterworth-Heinemann, 2001.

Part-time farming / Katie Thear. Publication info. London : Ward Lock Ltd., 1982.

Seven steps to a successful business plan / Al Coke. Publication info. New York : AMACOM, c2002.

Pick-your-own farming : cash crops for small acreages / Ralph L. Wampler and James E. Motes. Publication info. Norman : University of Oklahoma Press, c1984.

How to start, run, and stay in business / Gregory F. Kishel, Patricia Gunter Kishel. Publication info. New York : John Wiley, c1998.

The new farmers' market : farm-fresh ideas for producers, managers & communities / Vance Corum, Marcie Rosenzweig, and Eric Gibson. Publication info. Auburn, Calif. : New World Publishing ; [White River Junction, Vt. : Distributed by Chelsea Green Pub. Co.], c2001.

Dynamic farmers' marketing : a guide to successfully selling your farmers' market products / Jeff Ishee ; [foreword by Joel Salatin]. Publication info. Middlebrook, Va. : Bittersweet Farmstead, c1997.

The perfect business plan made simple / William R. Lasher. Publication info. New York : Broadway Books, c2005.

Anatomy of a business plan : a step-by-step guide to building a business and securing your company's future / Linda Pinson. Publication info. Chicago, IL : Dearborn Trade Publishing, c2001.

Small business survival book : 12 surefire ways for your business to survive and thrive / Barbara Weltman and Jerry Silberman. Publication info. Hoboken, N.J. : John Wiley & Sons, c2006.

---

Direct marketing of farm produce and home goods : direct marketing alternatives and strategies for beginning and established producers / John Cottingham ... [et al.]. Publication info. Madison, WI : University of Wisconsin--Extension, Cooperative Extension Service, [1994]

Facilities for roadside markets / by Arthur W. Selders ... [et. al.]. Publication info. Ithaca, NY : Northeast Regional Agricultural Engineering Service, Cooperative Extension, 1992.

Local flavors : cooking and eating from America's farmers' markets / Deborah Madison ; photographs by Laurie Smith ; illustrations by Patrick McFarlin. Publication info. New York : Broadway Books, c2002.

http://www.evergreen.edu/library/govdocs/coloringbooks/farmersmarket2.pdf

Eat here : reclaiming homegrown pleasures in a global supermarket / Brian Halweil. Publication info. New York : W.W. Norton, c2004.

Guide to planning the farm retail market : 1994 / Carl L. German ... [et al.]. Publication info. Newark, DE : University of Delaware, College of Agricultural Sciences, Agricultural Experiment Station, Cooperative Extension, [1994]

Virginia grown : a guide to pick-your-own and fresh-picked produce, honey, and retail farmers' markets. Publication info. [Richmond] : Virginia Dept. of Agriculture and Consumer Services,